## Operations Tracker
BUSINESS OPERATIONS TRACKER
Task Name | Assigned To | Start Date | Due Date | Status | Completion % | Priority | Remarks
Create employee database | Ravi Kumar | 01-Jun-25 | 10-Jun-25 | Completed | 100% | High | Done on time
Design onboarding form | Priya Nair | 03-Jun-25 | 12-Jun-25 | Completed | 100% | Medium | Reviewed by HR
Monthly expense report | Ankit Shah | 05-Jun-25 | 15-Jun-25 | In Progress | 60% | High | Pending approval
Update vendor contracts | Sneha Reddy | 07-Jun-25 | 20-Jun-25 | In Progress | 40% | Medium | Legal review pending
Prepare training materials | Darshan S | 08-Jun-25 | 22-Jun-25 | In Progress | 70% | High | Slides in progress
Customer feedback survey | Meera Joshi | 10-Jun-25 | 25-Jun-25 | Pending | 0% | Low | Not started
IT equipment audit | Rohit Verma | 11-Jun-25 | 28-Jun-25 | Pending | 0% | Medium | Scheduled
Q2 performance review | Ankit Shah | 12-Jun-25 | 30-Jun-25 | Pending | 0% | High | Awaiting data
Office supply procurement | Priya Nair | 02-Jun-25 | 08-Jun-25 | Completed | 100% | Low | Delivered
Website content update | Sneha Reddy | 05-Jun-25 | 18-Jun-25 | In Progress | 50% | Medium | Draft ready
SUMMARY DASHBOARD
Metric | Value | Metric | Value
Total Tasks | 10 | Completion Rate | 30%
Completed | 3 | High Priority | 4
In Progress | 4 | Avg Completion | 52%
Pending | 3 | Overdue Tasks | 0